## opportunity36_SRS_Review
SRS Review Sheet
| Project Name: | opportunity36
| Project Manager Name: | Manas Chattopadhay
| Reviewer: | Manas Chattopadhay
| Prepared by: | Manas Chattopadhay
| Review Date: | 10-08-26
| Approver: | Manas Chattopadhay
| Approval Date: | 10-10-26
ID | Doc. Cat. (SRS/SDD/PMP) | Doc. Name | Doc Version | Ref. Section | Defects | Recommendation | Severity | Status as on 08/10/2026 | Status as on 10/10/2026
1 | SRS of opportunity36 | opportunity36_srs.docx | 1.0 | 4.0 | The proposed system environments (Development, Testing, and Deployment) lack specific technical details, listing 'Not specified' for all software, hardware, and network requirements. | Define the technology stack (e.g., cloud provider, database engines, server-side frameworks) to ensure the infrastructure can support the functional requirements. | Major | Open
2 | SRS of opportunity36 | opportunity36_srs.docx | 1.0 | 6.0 | Non-functional requirements for 'Capacity Limits' and 'Data Retention' are marked as 'Not specified', which poses a risk to system scalability and regulatory compliance. | Define expected concurrent user loads and specify data retention policies in alignment with the mentioned data protection standards. | Major | Open
3 | SRS of opportunity36 | opportunity36_srs.docx | 1.0 | 5.2 | The 'University Application Submission' requirement lacks definition for mandatory fields other than 'University', such as student personal details or academic history. | Expand the 'fields' section in FR-002 to include all necessary data points required for a complete university application. | Minor | Open
4 | SRS of opportunity36 | opportunity36_srs.docx | 1.0 | 7.0 | The 'Inter-functional Data Definitions' and 'Component Cross-Reference' sections are empty, hindering the understanding of how data flows between the various modules (e.g., Admissions vs. Training). | Document the data mapping and dependencies between modules to ensure consistent data handling across the platform. | Minor | Open