## Sheet1
Serial No. | Business Objective | Description | Procedure in brief | Related Metrics | QPPO - Goal/KPI | Tracking & monitoring interval | Guiding Note
1 | Fulfil Delivery Commitments | Meeting delivery commitments is a major key to success in enhancing business and customer loyalty. So, that should be a priority. | Actual delivery time should always be monitored vis-à-vis the committed delivery schedule and any slippage thereof should always be minimised. | Schedule Variance - Revised (in %) | USL: 5% LSL: -5% | At every significant delivery milestone | For Development, Enhancement, Migration etc type of job
1 | Manage projects within budget | As the project cost may depend on various factors including and other than cost of effort it is essential that the project cost is contained within the approved estimated effort. | Effort use should be optimized so that project could be delivered within schedule and within budget | Cycle Time measures person-hour needed to produce 1 unit size (UCP) [decrease in value is poistive] | Mean 14/ SD 1 | At every significant delivery milestone | For Development, Enhancement, Migration etc type of job
2 | Ensure quality of products delivered to customer - for software development projects | Ensure that defects in products delivered to customer for their perusal (including UAT) are always at a minimum level. That is another major key to achieving customer satisfaction, customer loyalty, and building company goodwill. | Defect Removal Efficiency measures ratio between all the review and testing defects found by us and (all the review and testing defects found by us + UAT defects ) | DRE [increase in value is poistive] | Mean: 0.9/ SD 0.1 | After UAT of every release | For Development, Enhancement etc type of job
4 | Improve quality of software engineering while the products are being made ready for delivery | Productivity and cost in a software project would always depend on the quality of engineering work being done. So, that should be closely monitored. | Pre-delivery Defect Rate is computed from the total number of defects detected by the project team for every product release through various review and testing activities that take place before the software is delivered for UAT. | Average Pre-delivery Defect Rate (No. of defects per Person Hour) | USL : 1 defects per Person hour LSL: 0 defects per Person hour | Before/after every product release | For Development, Enhancement etc type of job
3 | Continually Improve productivity | Improving the productivity of the project team is key to minimizing project cost and the time to market. So, major focus should be on maximising productivity. | productivity should be measured in terms of software size delivered Vs. effort spent in software engineering. | productivity (UCP per Person-Hour) [increase in value is poistive] | productivity (UCP per Person-Hour) target mean 0.07 UCP/p-h and 0.01 SD for the year 23-24 | After UAT of every product release - or complesion of each Use-Case | For Development, Enhancement etc type of job