## opportunity36_SDD_Review
SDD Review Sheet
| Project Name: | opportunity36
| Project Manager Name: | Manas Chattopadhay
| Reviewer: | Manas Chattopadhay
| Prepared by: | Manas Chattopadhay
| Review Date: | 10-08-26
| Approver: | Manas Chattopadhay
| Approval Date: | 10-10-26
ID | Doc. Cat. (SRS/SDD/PMP) | Doc. Name | Doc Version | Ref. Section | Defects | Recommendation | Severity | Status as on 08/10/2026 | Status as on 10/10/2026
1 | SDD of opportunity36 | opportunity36_sdd.docx | 1.0 | 2.0 | The development, testing, and deployment environment sections are entirely empty, lacking specifications for technology stacks, hardware, or network requirements. | Define the specific technology stack (e.g., Java/Spring Boot, Node.js), database systems (e.g., PostgreSQL), and infrastructure requirements (e.g., Cloud provider, containerization) to ensure architectural feasibility. | Major | Open
2 | SDD of opportunity36 | opportunity36_sdd.docx | 1.0 | 3.4 | The sequence diagram for Course Registration and Payment shows a direct interaction between the controller and the payment gateway, but lacks error handling or rollback mechanisms for failed transactions. | Update the sequence diagram and business rules to include a compensation flow or transaction rollback mechanism in the event of a payment gateway failure to ensure data consistency in the Enrollment Repository. | Major | Open
3 | SDD of opportunity36 | opportunity36_sdd.docx | 1.0 | 5.0 | The database design is described only as a 'logical separation' without providing an Entity Relationship Diagram (ERD) or schema definitions for the proposed modular architecture. | Include a formal ERD illustrating the relationships between User, Application, Enrollment, and Content entities to validate the modularity and data integrity of the system. | Minor | Open
4 | SDD of opportunity36 | opportunity36_sdd.docx | 1.0 | 6.0 | System implementation and database administration procedures are listed as 'Not specified', creating a gap in the operational readiness of the platform. | Document the CI/CD pipeline strategy, database migration procedures, and backup/recovery protocols to ensure the system can be reliably deployed and maintained. | Major | Open